## _PMO Remediation Export
(Do Not Modify) Risk Strategy Recommendation | (Do Not Modify) Row Checksum | (Do Not Modify) Modified On | Environment | VRAS Name | Vendor Security Risk Strategy Recommendation | Documentation Request | Risk Reduction Impact | Recommended Due Date | Remediation Strategy Accepted by Vendor | Contractually Agreed Upon Completion Date | Vendor Notes | Risk Strategy Status | Key Control (Questionnaire Template Item Lookup) (Questionnaire Template Item)
c42c57be-7fcc-ec11-a7b5-000d3a32e0ed | hutllSc6qOzkWVU7PbtNB4fb8HtA14P6nzpKXVyR21R854rMgnlpGZGtCEI9YNLd+m07vJbeXW+fihkd4xiq8w== | 2022-05-17 19:30 | PeriWatch (On-Prem) | VSRM for: Avera Health / PeriGen | CVR-SEC CERT-1.2 Obtain a third-party audit (preferably SOC 2 Type 2 TSP at a minimum Security, Privacy and Confidentiality, HITRUST or ISO 27001) within 12-18 months specific to the application. A readiness report should be provided within 6 months. |  | High | 2023-12-31 | No |  | Since the product developed by PeriGen is fully hosted/manages by the customer infrastructure, SOC2 is more applicable at the custome side. PeriGen is looking for SOC2 certification for the transition into cloud service offering when we do directly manage customer data. | Sent to Vendor
fb7a7164-bac7-ec11-a7b6-6045bd00f029 | JxsXt9w3leEu8A5MgdgfvWZh5UANDNfEPnbSHfbBlFClT0dywbs4YYVKk4Z/fRLTVqAfy1Ci1gJl5145L1XqZA== | 2022-05-17 19:30 | PeriWatch (On-Prem) | VSRM for: Avera Health / PeriGen | CM-6.3 Implement procedures for documenting and approving deviations from established configuration settings for the information system. | Provide documentation of monitoring records related to most recent changes to the Configuration settings information system or system generated list of configuration changes. | High | 2022-09-30 | Yes |  | We already have this in place for the PeriGen side of product life-cycle. | Sent to Vendor
fc7a7164-bac7-ec11-a7b6-6045bd00f029 | oc2aUl+joQHMckiOE9OoQ3FXjW3EYbmwABsBz4539knLwW+HA8PvIY0dRrL7mN61lamjLXdCVjxh+7FRzm8D2g== | 2022-05-17 19:30 | PeriWatch (On-Prem) | VSRM for: Avera Health / PeriGen | CM-9.1 Develop an adequate configuration management plan for the information system that addresses roles, responsibilities and configuration management processes and procedures. | Provide Software Development/Deployment Life Cycle (SDLC) Policy, and procedures Provide secure coding procedures, where applicable. Provide secure coding checklists where applicable. Evidence of the most recently completed secure coding checklist | High | 2022-09-30 | Yes |  | We already have this in place. Policy was already sent | Sent to Vendor | Yes
fd7a7164-bac7-ec11-a7b6-6045bd00f029 | DKkjIJGZkHVO9ZuJMgN81ophn/7urcoIZB8a3nKv0B+wEqIXZP/19Btc6/YWYwygTmGZu0eMh36JE4E8tS/dCQ== | 2022-05-17 19:30 | PeriWatch (On-Prem) | VSRM for: Avera Health / PeriGen | IA-5.2 Enforce password requirements to comply with the following: - Passwords at least 8 characters in length - Passwords are created using the following: - Mixed case alpha characters - at least one numeric digit - at least one non-alphanumeric character - Current password may not be reused - Current passwords expire every 90 days - Passwords stored in an encrypted format | Provide Policy regarding password Parameter settings. For in-scope systems, provide system generated list and/or screen print of password parameter settings. | High | 2022-09-30 | Yes |  | We already responded that this is fully supported and being that virtually all customers use AD integrated authentication, this is already managed by the customer | Sent to Vendor | Yes
5f7b7164-bac7-ec11-a7b6-6045bd00f029 | jtLumo2QBWfVFeP0UEmoprDbUhXLJ7zaGMyjQdLfhJfLKEiin1RuhePDV3AIBITqJPcTGptLDUvk5ad5Gy+LfA== | 2022-04-29 12:47 | PeriWatch (On-Prem) | VSRM for: Avera Health / PeriGen | PS-6.1 Implement access agreements that are reviewed annually for individuals with access to the information system. |  | Low | 2022-09-30 |  |  |  | Open
607b7164-bac7-ec11-a7b6-6045bd00f029 | ok4udfcL6fIg9Mo0MoZwR/f849p3/7MawQz7/v6+v5TpDtGosr9+yrzwZHUkHUP8MAoVofGEJtjmoyfYvHSgWA== | 2022-04-29 12:47 | PeriWatch (On-Prem) | VSRM for: Avera Health / PeriGen | SI-1.1 Develop and implement policies and procedures for System and Information Integrity. |  | Low | 2022-09-30 |  |  |  | Open
b50f6270-bac7-ec11-a7b6-6045bd00f029 | SgsTobGoAHSg9cMiF+aBbcyFE/grHZegD4s7EzDd49f0l0ZHMHNaOtmGrhvvBodveoNGsP/yx8528GNQvF7MHw== | 2022-04-29 12:47 | PeriWatch (On-Prem) | VSRM for: Avera Health / PeriGen | SC-10.1 Configure the information system to terminate network connections associated with a communication session at the end of the session or after no longer than 30 minutes of inactivity. |  | Low | 2022-09-30 |  |  |  | Open
b70f6270-bac7-ec11-a7b6-6045bd00f029 | oBNi81K8Pu+pCorAm1s3BrepPoo9Sk40b+aDSjkjfUbF586nZKqNNL4dlWCqr5ZH1yXvLkzzdgmaDgokezcREw== | 2022-04-29 12:47 | PeriWatch (On-Prem) | VSRM for: Avera Health / PeriGen | SC-20.1 Require the information system to provide additional data origin authentication and integrity verification artifacts along with the authoritative name resolution data when the system returns responses to external name/address resolution queries. |  | Low | 2022-09-30 |  |  |  | Open
2a5bcb66-bac7-ec11-a7b6-6045bd00f051 | E0iERKYS91M+1via9t3Z1yYRX+GW3k2yRuU0wCCHoOQegd+iKPgtN8dQ3TKZhMuS1HvTwTxEOIZOcjwYnPiJ7g== | 2022-05-17 19:30 | PeriWatch (On-Prem) | VSRM for: Avera Health / PeriGen | CM-2.1 Develop a configuration baseline for the information system. | Provide policy and procedure as it pertains to baseline configurations. Provide the most recent Baseline Configuration document for the information systems in scope for review. (e.g., hardening procedures for Window OS, baseline security settings for sever AND application builds.) Provide evidence to support compliance with configuration baselines. This may be verified by evidence of testing documentation when the system was implemented or results of a recent audit, etc. | High | 2022-09-30 | No |  | OS configuration/baseline/hardening is the reposnsibility of the customer. PeriGen only provides the system requirement to run the PeriGen product. | Sent to Vendor | Yes
01335f6f-bac7-ec11-a7b6-6045bd00f051 | E5vQQ1eFF7SN5Gm14w7g/GJTgTsGPr+fwmNWUEJOmwJ8eC8wT/75pK3SlkMvLlB6/3jaW0zwSZ2pjeNMLytGoA== | 2022-05-17 19:29 | PeriWatch (On-Prem) | VSRM for: Avera Health / PeriGen | CM-14.2 Implement patches categorized as "critical" within 72 hours of patch release. | Provide Patch Management Policy/Procedure Provide Change control Policy procedure Provide evidence of implemented patches for the prior three months | Medium | 2022-09-30 | Yes |  | For PeriGen patches, we do have these policies implemented. OS level patches are the responsibility of the customer who manages the servers/workstations where the application is installed. | Sent to Vendor
02335f6f-bac7-ec11-a7b6-6045bd00f051 | fGUcPStRvgp9qH7D8lLADDOQh96zY+uKR7Jfysk+Pgj4UG0LP6YX5buuPtkt2sWWMKTASSOQBBCSPhFLmFEPaw== | 2022-05-17 19:29 | PeriWatch (On-Prem) | VSRM for: Avera Health / PeriGen | IR-3.1 Conduct incident response tests. | Provide completed Incident response testing, results and issues list | Medium | 2022-09-30 |  |  |  | Sent to Vendor
09335f6f-bac7-ec11-a7b6-6045bd00f051 | rQo8CsfacKTJTHV5NpzPuKk3nTNm7wY9rDL25xLZJKc460VbCz2ZIukJpYroqmbS/ycyF+UAT34EkFDLVjv8zg== | 2022-04-29 12:47 | PeriWatch (On-Prem) | VSRM for: Avera Health / PeriGen | IA-7.1 Implement mechanisms for the information system to authenticate to cryptographic modules. |  | Low | 2022-09-30 |  |  |  | Open
0c335f6f-bac7-ec11-a7b6-6045bd00f051 | t7nzU20NxHkc4LH7PRBkX3M+jIZzNchrx8HnbfUF4RmyBAkrMmfDsKzsZOM6h0Pop6ZLuZyyOon3zP7UOueG8A== | 2022-05-17 19:29 | PeriWatch (On-Prem) | VSRM for: Avera Health / PeriGen | IA-3.1 Configure the information system with the capability to uniquely identify and authenticate devices before establishing a connection. | Provide policy for device identification and authentication. Provide documentation that demonstrates all devices are uniquely identified during authentication to information system. | Medium | 2022-09-30 |  |  |  | Sent to Vendor
0d335f6f-bac7-ec11-a7b6-6045bd00f051 | /QzJpfEVpBZsADqKet/NG7WwGRHIcTOdMAgYEWbKcJlaIOVh2+Y540pXQf/eGv8QYknsuLCI+FMTndXtr15VPg== | 2022-05-17 19:29 | PeriWatch (On-Prem) | VSRM for: Avera Health / PeriGen | CM-14.1 Implement processes to categorize patches based on severity. | Provide Patch Management Policy/Procedure Provide Change control Policy procedure Provide evidence of implemented patches for the prior three months | Medium | 2022-09-30 |  |  |  | Sent to Vendor
14335f6f-bac7-ec11-a7b6-6045bd00f051 | wf6FoXsqOZGWOZbAvtzJY7U0zrGz8Y76rLwxLTdwKvecZpNC60Nt0r78r0RsFk1I4hBPUpxPg/o3oOOYiSWlCQ== | 2022-04-29 12:47 | PeriWatch (On-Prem) | VSRM for: Avera Health / PeriGen | MA-2.5 Require the organization to validate that all security controls are functioning properly following maintenance and/or repairs. |  | Low | 2022-09-30 |  |  |  | Open
15335f6f-bac7-ec11-a7b6-6045bd00f051 | BH/5Y0oplEWedtdeFa8ATPtoUgtfgYmxQjt6Zh5g1IPn9VaiZHhrz7paRn1TWzWx9USwG32fvnvi/rHmJwozTQ== | 2022-05-17 19:29 | PeriWatch (On-Prem) | VSRM for: Avera Health / PeriGen | AU-3.1 Configure the information system to generate sufficient audit records for investigation. | Provide Policy/Procedure/process for Auditing Events. Provide Policy/Procedure/Process for monitoring event logs Provide Configuration documentation for applicable in scope systems, showing configurations of audit settings, time clocks and clock synchronization. Provide evidence of audit logs and related monitoring activities along with any incident response for the previous three months for applicable in scope systems. | Medium | 2022-09-30 |  |  |  | Sent to Vendor
1d335f6f-bac7-ec11-a7b6-6045bd00f051 | oPCAt61vb1EaVeSyMJ5XIHB42IcsEWr0+4GdsrkDYdRwNXkCe1H9iwU430XMhpOTUsto3r/Ab0lnq2TQjJcOOQ== | 2022-05-17 19:29 | PeriWatch (On-Prem) | VSRM for: Avera Health / PeriGen | IR-2.2 Provide Incident response training that is unique to the role of the individual. | Provide evidence of completed incident response training. | Medium | 2022-09-30 |  |  |  | Sent to Vendor
41335f6f-bac7-ec11-a7b6-6045bd00f051 | IW0STfUbhVDwYLIc6jMdNHwmwWZGv4i0L+tRzQoUtmTiWaiRO5/a1UbUb95M0urJ1dMGAm+UKD+4RlzT9heeIw== | 2022-04-29 12:47 | PeriWatch (On-Prem) | VSRM for: Avera Health / PeriGen | PS-2.1 Assign risk designations to all positions. |  | Low | 2022-09-30 |  |  |  | Open
b4335f6f-bac7-ec11-a7b6-6045bd00f051 | jsHuQIWO8uE6i9eBqmBptKNpZWcJ/N9tbzTb2ltTDnsHvhL8yuYeOoIo3hyU3nf1pTDC7Y9vvCjiKV5XTJU7tg== | 2022-04-29 12:47 | PeriWatch (On-Prem) | VSRM for: Avera Health / PeriGen | PS-2.3 Implement processes for reviewing and revising position risk designations at least every three years. |  | Low | 2022-09-30 |  |  |  | Open
b7335f6f-bac7-ec11-a7b6-6045bd00f051 | +/uEqs3ySRO/2Xi6z4H2qPFmhM9p/8+WCRSb6YguVupdRzthuFiljIMgIhRZlePvZ9GDoVmZAT/He+Es5UgHig== | 2022-05-17 19:29 | PeriWatch (On-Prem) | VSRM for: Avera Health / PeriGen | SA-11.1 Require the developer of the information system to create and implement a security assessment plan, perform tests/evaluations and produce evidence of the execution of the security assessment plan. | Please provide the developer's security assessment plan and copies of tests/evaluations that demostrates of the execution of the security assessment plan? | Medium | 2022-09-30 |  |  |  | Sent to Vendor
b8335f6f-bac7-ec11-a7b6-6045bd00f051 | G3AuBRUX5QSuKnC/TYjYsOiLomt7Or548GSVodd80O/MpG+dJDkwT/uJggW+VcY6OQcNWDA6AaBr8EFm4bbh5w== | 2022-05-17 19:29 | PeriWatch (On-Prem) | VSRM for: Avera Health / PeriGen | IR-3.2 Analyze incident response tests. | Provide completed Incident response testing, results and issues list | Medium | 2022-09-30 |  |  |  | Sent to Vendor
c4335f6f-bac7-ec11-a7b6-6045bd00f051 | xUqdE9KWgrYaeyxatuQiVMsdYc0Yp01jilm0NGex9C2MLSIJ5Sjq0sUkMrOjVXVOJ50zHB3dSUDuD9+8T3SN5A== | 2022-04-29 12:47 | PeriWatch (On-Prem) | VSRM for: Avera Health / PeriGen | AU-5.1 Configure the information system to generate an alert to notify the team in the event of an audit processing failure. |  | Low | 2022-09-30 |  |  |  | Open
cc335f6f-bac7-ec11-a7b6-6045bd00f051 | naQsoLNvHfvoHlm4IoaA+i/Ra5zxV7kZjwzRVWct3r6vnVCdTNhJX2bIq+VzWNJek4omtdr1GCtfjk2OROj2RQ== | 2022-04-29 12:47 | PeriWatch (On-Prem) | VSRM for: Avera Health / PeriGen | AU-12.1 Configure the information system with the capability to select which auditable events are captured in the audit log. |  | Low | 2022-09-30 |  |  |  | Open
d4335f6f-bac7-ec11-a7b6-6045bd00f051 | Ig+R3DA6G+u3azU1i/A0VvBxsmesno5BXxPTYk99BwDi5RrZzx6nxJZ3AB9Vh5UsTFEwxPEDP3agXkxmy1e53w== | 2022-04-29 12:47 | PeriWatch (On-Prem) | VSRM for: Avera Health / PeriGen | CM-12.2 Require the organization to develop and implement policies that define the timing for applying patches to the information system. | Provide Patch Management Policy/Procedure Provide Change control Policy procedure Provide evidence of implemented patches for the prior three months | Low | 2022-09-30 |  |  |  | Open
d9335f6f-bac7-ec11-a7b6-6045bd00f051 | xGhj68KZPGdTu6aqY5+hB2Sk5Ik5HlTzZ8Kv+PAAjxxaDQzPHAAm8CTJA4lHGpSJ48vdJcN1oHJgqcuLdtfQpw== | 2022-04-29 12:47 | PeriWatch (On-Prem) | VSRM for: Avera Health / PeriGen | IA-4.2 Configure the information system to prevent reuse of user or device identifiers. |  | Low | 2022-09-30 |  |  |  | Open
ed335f6f-bac7-ec11-a7b6-6045bd00f051 | 8jrveOXKAg/xDgpRVzQFfobIYi0WDPQZRexm6i3IsHwEwhKcndojl4/olgiUvlJA8qe4Ir13SL6G91nc1ul6XQ== | 2022-04-29 12:47 | PeriWatch (On-Prem) | VSRM for: Avera Health / PeriGen | IA-5.9 Require token-based authentication for access to the information system. | Single Sign On configuration settings. | Low | 2022-09-30 |  |  |  | Open
08345f6f-bac7-ec11-a7b6-6045bd00f051 | KOoDahitDpPny3oQMXhM5P9XKo7QFwK5vhehGHVa2kGNC2qjTSQNdQdcEESyUor+/MCUH0qX0Gaw6QI8y4zb0Q== | 2022-04-29 12:47 | PeriWatch (On-Prem) | VSRM for: Avera Health / PeriGen | AC-8.1 Implement system use notifications that provide privacy and security notices before granting access. | Is there a system use notification displayed before granting access that provides privacy and security notices? | Low | 2022-09-30 |  |  |  | Open
0c345f6f-bac7-ec11-a7b6-6045bd00f051 | AgT0rvlwUELdZyFqJRUPSgMbBGKEIUKe++lubeCopmoRw5yDjYcpKA3wpCLhnMVn7O5WIigy4qVaLi9hMMniVw== | 2022-04-29 12:47 | PeriWatch (On-Prem) | VSRM for: Avera Health / PeriGen | SC-23.1 Implement controls for protecting the authenticity of communication sessions. |  | Low | 2022-09-30 |  |  |  | Open
20345f6f-bac7-ec11-a7b6-6045bd00f051 | 42fAKD6H593SMF2kBYT60y3dmTZzLOjYH+O6Rex2f7Gc8aGjafj2PXQPO9YeQFZ2I9SjfN0obJu5tZewwHbt+Q== | 2022-04-29 12:47 | PeriWatch (On-Prem) | VSRM for: Avera Health / PeriGen | AC-9.1 Configure the system to display the previous date and time of a user's last login. |  | Low | 2022-09-30 |  |  |  | Open
26345f6f-bac7-ec11-a7b6-6045bd00f051 | 5SAllN8uHjkZ1KTZpl4Y20TOv4AVaE6jiHJSuDDtnCTngXkCDGiIShN2xkrQFjxRDxoESH7JiGrhMQiP3YnAOQ== | 2022-04-29 12:47 | PeriWatch (On-Prem) | VSRM for: Avera Health / PeriGen | AC-10.1 Configure the system to limit the number of concurrent sessions for users. | 1) Screenshot of Active Directory Group Policy (GPO) Settings 2) Screenshot of Active Directory Configuration | Low | 2022-09-30 |  |  |  | Open
48345f6f-bac7-ec11-a7b6-6045bd00f051 | /MZ8duLDshdquQw9iI8i8kWbQPhrO/Kc4nkGXMAn6GeT2HsmvTBLc9LYj5ZtJXBxFWas44/fa/BS8B+S+1uGhg== | 2022-04-29 12:47 | PeriWatch (On-Prem) | VSRM for: Avera Health / PeriGen | PS-3.2 Implement processes to re-screen individuals with access to the information system. | Provide policy regarding Hiring/Onboarding Requirements Please provide redacted copies of screening reports for the past 6 months | Low | 2022-09-30 |  |  |  | Open
4d345f6f-bac7-ec11-a7b6-6045bd00f051 | 3teOY4sIiMjeNEUcJ8GURRae4e5PZfNVqwJMFHeoH7lL1arzVrCTcOCdUhJv2GOMnP590VYZjPvDI7tHmBNQTw== | 2022-04-29 12:47 | PeriWatch (On-Prem) | VSRM for: Avera Health / PeriGen | SA-1.1 Develop and implement formally documented policies and procedures for System and Services Acquisitions. |  | Low | 2022-09-30 |  |  |  | Open
55345f6f-bac7-ec11-a7b6-6045bd00f051 | OaQn6DImhkeIwpIBPWCxx98oes2jqDFw9iHG2at31dpOLanxBUOFSj1m29un1P97B4fzjN/38LV6JJwyNIpUOA== | 2022-04-29 12:47 | PeriWatch (On-Prem) | VSRM for: Avera Health / PeriGen | SA-5.4 Protect information system documentation as required and only distributed to authorized personnel. |  | Low | 2022-09-30 |  |  |  | Open
64345f6f-bac7-ec11-a7b6-6045bd00f051 | nR581cNQ6P65sHjkRh1e7Tbxm4kUelgSO27c/DXyTiiK789xG95CKBeBKJikZPNwyPKsfJj2RAAWEuG8jp5+KQ== | 2022-04-29 12:47 | PeriWatch (On-Prem) | VSRM for: Avera Health / PeriGen | SC-1.1 Develop and implement policies and procedures for System and Communications Protection. |  | Low | 2022-09-30 |  |  |  | Open
e42c0f67-bac7-ec11-a7b6-6045bd00f110 | tk9RZcY5FJeRAvj7n+e8Vdfa/68h0h8jAh7oy8+9lO2M5CB4SzCACUX1otnPbTtFIOxfc6vhQDEj0tUE6lw8sg== | 2022-04-29 12:47 | PeriWatch (On-Prem) | VSRM for: Avera Health / PeriGen | PS-5.1 Implement appropriate transfer procedures for those with access to the information system. | Provide Transfer policy, procedure, process. | Low | 2022-09-30 |  |  |  | Open
a2b65763-bac7-ec11-a7b6-6045bd00f3d4 | zxxni/wANX3PSjIHXjv0Zp8KvSFHWqrXOPhD8zZroB/nYhAbOVBVtuVANZUbQbZK+pIvubILkMbSIZsbWKL3bA== | 2022-05-17 19:30 | PeriWatch (On-Prem) | VSRM for: Avera Health / PeriGen | IA-5.3 Encrypt passwords within the information system when stored or transmitted. | Please provide screen shot of configuration settings that demonstrates passwords are not stored in clear text. | High | 2022-09-30 |  |  |  | Sent to Vendor
8182816f-bac7-ec11-a7b6-6045bd00f3d4 | GWTiajEVSRwz81oUujX3xmW5+Ogjou1hOzY5ZQbfKVuQ8aiy4Q3SOXD2r9gP1ezgxeiBzPTZmQzjTBaDyxd9dg== | 2022-04-29 12:47 | PeriWatch (On-Prem) | VSRM for: Avera Health / PeriGen | SC-21.1 Require the information system to request and perform data origin authentication and data integrity verification on the name/address resolution responses that the system receives from authoritative sources. |  | Low | 2022-09-30 |  |  |  | Open
38e17861-bac7-ec11-a7b6-6045bd00f55c | jYBCu52BMpT8DeNvjwsl5UF6s8MT49/NysWcf8Un51vzjsGI5iWZWVEXvWw9I0xm3bdGdvYmH08glxwhCffOvQ== | 2022-05-17 19:30 | PeriWatch (On-Prem) | VSRM for: Avera Health / PeriGen | CM-6.2 Implement mechanisms for automated or manual monitoring of configuration changes to the information system. | Provide documentation of monitoring records related to most recent changes to the Configuration settings information system or system generated list of configuration changes. | High | 2022-09-30 |  |  |  | Sent to Vendor
3be17861-bac7-ec11-a7b6-6045bd00f55c | 4dr55GJwecDR0g57YoM1OpFv8KhO4GEdy2rhbXM7/LcEvd+/1F+NxNHC30qg6aBYidLmHOmJlxeel435EvqrXQ== | 2022-05-17 19:30 | PeriWatch (On-Prem) | VSRM for: Avera Health / PeriGen | CM-3.5 Retain records of configuration controlled changes. | Configuration Change Control procedures List of Configuration Changes and supporting evidence for the previous 3 months. Log showing when/where the change occurred (as applicable) | High | 2022-09-30 |  |  |  | Sent to Vendor
3ce17861-bac7-ec11-a7b6-6045bd00f55c | uu0dUH8mgSnrBrChtUautt9MROP/2aYtB0GHhzKpfDJpVwUpZKUM6gxGh1t1qcS2gxpTZzGYq3nnj7J7ppcTQg== | 2022-05-17 19:30 | PeriWatch (On-Prem) | VSRM for: Avera Health / PeriGen | CM-3.6 Implement auditing and monitoring activities to assess configuration-controlled changes to the information system. | Configuration Change Control procedures List of Configuration Changes and supporting evidence for the previous 3 months. Log showing when/where the change occurred (as applicable) | High | 2022-09-30 |  |  |  | Sent to Vendor
45e17861-bac7-ec11-a7b6-6045bd00f55c | tcAXLUWFLoOAUZk8O2hUqoe+JlpFWyBEusZpDNj88ZR+05HJkKY0YImwPUa9Gr6a5EcN1NBWulT8Dh/4ug8tUw== | 2022-05-17 19:30 | PeriWatch (On-Prem) | VSRM for: Avera Health / PeriGen | CM-6.1 Document and implement configuration settings for the information system that reflect the most restrictive mode consistent with operational requirements. | Provide documentation of monitoring records related to most recent changes to the Configuration settings information system or system generated list of configuration changes. | High | 2022-09-30 |  |  |  | Sent to Vendor
47e17861-bac7-ec11-a7b6-6045bd00f55c | myIsDeS4Ryb6nTSPFfz0bDaAGwdQ1M6h5lTye5A3KWitJEAseiXHMjAKurmfE+cC9okvqlv+crPj5Jaw8GnqVA== | 2022-05-17 19:30 | PeriWatch (On-Prem) | VSRM for: Avera Health / PeriGen | CM-3.3 Adequately document all configuration changes to the information system. | Configuration Change Control procedures List of Configuration Changes and supporting evidence for the previous 3 months. Log showing when/where the change occurred (as applicable) | High | 2022-09-30 |  |  |  | Sent to Vendor
3391ba63-bac7-ec11-a7b6-6045bd00f6a1 | oYpjvCynQES4gCJGqZTBpjg8zm7ug4B8bexseeRFLj4hQZqZZ6/YAK5g/7vtg/KL5lEJF8+b01JzC52MQa1IBQ== | 2022-05-17 19:30 | PeriWatch (On-Prem) | VSRM for: Avera Health / PeriGen | CM-3.1 Define configuration-controlled changes for the information system. | Configuration Change Control procedures List of Configuration Changes and supporting evidence for the previous 3 months. Log showing when/where the change occurred (as applicable) | High | 2022-09-30 |  |  |  | Sent to Vendor | Yes
bce7c569-bac7-ec11-a7b6-6045bd00f6a1 | 4YucGslR31abU8hiXxUyllfSKetI1jFWUQkYk1cnKNJQbL8R3Kl47X4bNZBoO41T+MHaKmf5fDokyDQHb2k5Kg== | 2022-04-29 12:47 | PeriWatch (On-Prem) | VSRM for: Avera Health / PeriGen | SA-5.1 Develop administrator documentation that describes: 1 Secure configuration, installation, and operation of the system, component, or service; 2 Effective use and maintenance of security functions/mechanisms; and 3 Known vulnerabilities regarding configuration and use of administrative (i.e., privileged) functions; |  | Low | 2022-09-30 |  |  |  | Open
15b77d66-bac7-ec11-a7b6-6045bd00f841 | +aWR6oL0QG6wCg5kb+49nTBAK5ZM72eu4IEOscip8zYrR0oImQjLg/+89QyCPhXwNWBp04K9hMY2DT6BNMIYYg== | 2022-05-17 19:30 | PeriWatch (On-Prem) | VSRM for: Avera Health / PeriGen | MA-4.2 Implement procedures to monitor all nonlocal maintenance and diagnostic activities. | Provide Policy, procedure and process for performing non-local maintenance activities. Provide supporting documentation evidencing maintenance and/or diagnostic services over the prior three months. Provide List of ID's with Access to remote functions for applicable systems along with their access rights and last log in date. | High | 2022-09-30 |  |  |  | Sent to Vendor | Yes
7baac263-bac7-ec11-a7b6-6045bd00fa65 | 0ajE9jikVjAh1kn2b3i8NY8l3DuXKnD9Im1SWtBJl0Zp2AS7ps5QpDzhdpe+FML2y+W7V9xVBDfNdnYh+U4TFA== | 2022-05-17 19:30 | PeriWatch (On-Prem) | VSRM for: Avera Health / PeriGen | SI-2.1 Identify, report, and correct information system flaws (ex. Perform and address vulnerability scans). | Provide Security Remediation Polices/Procedures and Processes. Provide results of vulnerability and penetration testing. Provide supporting evidence of remediation activities of all high risk issues identified within the vulnerability and penetration testing. Provide documentation that all identified high risk vulnerabilities are remediated in a timely manner. | High | 2022-09-30 |  |  |  | Sent to Vendor | Yes
7eaac263-bac7-ec11-a7b6-6045bd00fa65 | Zr4ZN4PZFBFx6ikxheUW9aD7scw4BQaDD73DzhFavNEIzTyV6NXDOSrsA7yIKOPZt4CzdqIwyh4TRs85RY6o/w== | 2022-05-17 19:30 | PeriWatch (On-Prem) | VSRM for: Avera Health / PeriGen | SC-8.2 Implement cryptographic mechanisms to recognize changes to information during transmission. | Provide policies/procedures regarding security of data transmission Provide Policy/Procedures for data encryption Provide screen shot of server supported encryption protocols. | High | 2022-09-30 |  |  |  | Sent to Vendor
b4aac263-bac7-ec11-a7b6-6045bd00fa65 | VWHYSv4Fe90hm/UjzTmVL4pgm3eCb3qsdMOPL1iLcehKHgZQxNyYjI30MXB1+6lYOATY2rE0lMCorVmRdbBwcQ== | 2022-05-17 19:29 | PeriWatch (On-Prem) | VSRM for: Avera Health / PeriGen | AT-3.1 Perform role-based security training for personnel with assigned security roles and responsibilities for the information system before access is granted. | Provide Security Awareness and Training Policy and procedure Provide Evidence of annual security awareness and training results | Medium | 2022-09-30 |  |  |  | Sent to Vendor
bb79c469-bac7-ec11-a7b6-6045bd00fa65 | UabHKJSquGK3cAEN4tn4/XePrsNGVLtEF8Ly+sJcGhjVxOi8JsIN5LBfsgpDy057bXbo+OpF940F02WDXSvZRA== | 2022-05-17 19:29 | PeriWatch (On-Prem) | VSRM for: Avera Health / PeriGen | AC-12.1 Configure the information system to terminate user sessions after predefined circumstances. | Documented policy regarding session timeouts Print screen showing the configuration settings for session timeouts not associated with inactivity | Medium | 2022-09-30 |  |  |  | Sent to Vendor
c279c469-bac7-ec11-a7b6-6045bd00fa65 | 6XmSPgE6A4EWpONVFF38+btgPYvV4UgKOAiUyd0L87xjZ95zvMsdntc4RZ1qR0JwYzPjk801h+biZ2QeyMRhDQ== | 2022-04-29 12:47 | PeriWatch (On-Prem) | VSRM for: Avera Health / PeriGen | IA-2.1 Implement multi-factor authentication for privileged and non-privileged access. | Provide supporting evidence to substantiate multi-factor authentication is implemented. | Low | 2022-09-30 |  |  |  | Open

## hiddenSheet (hidden)
ct_vrasriskstrategyrecommendation:IQJ/M4vVxMoXWDu2Qha2ovWG/BDV0L7EAqE9AwQPYADBVufJlEdYAw3q31D9FQkJtuCXxDfV8gfGZawgI6Z31w==:ct_vrasriskstrategyrecommendationid=%28Do%20Not%20Modify%29%20Risk%20Strategy%20Recommendation&checksumLogicalName=%28Do%20Not%20Modify%29%20Row%20Checksum&modifiedon=%28Do%20Not%20Modify%29%20Modified%20On&ct_environment=Environment&ct_vrasid=VRAS%20Name&ct_vendorsecurityriskstrategyrecommendation=Vendor%20Security%20Risk%20Strategy%20Recommendation&ct_documentationrequest=Documentation%20Request&ct_riskreductionimpact=Risk%20Reduction%20Impact&ct_recommendedduedt=Recommended%20Due%20Date&ct_remediationstrategyacceptedbyvendor=Remediation%20Strategy%20Accepted%20by%20Vendor&ct_contractuallyagreeduponcompletiondate=Contractually%20Agreed%20Upon%20Completion%20Date&ct_vendornotes=Vendor%20Notes&ct_newriskstrategystatus=Risk%20Strategy%20Status&4685eed9-427a-4946-8caf-e19971aca49a.ct_keycontrol=Key%20Control%20%28Questionnaire%20Template%20Item%20Lookup%29%20%28Questionnaire%20Template%20Item%29
Yes | No
Open | Client Accepted Risk | Deferred | Sent to Vendor | Accepted | Not Accepted | Vendor Nonresponsive | Vendor Follow Up | Evidence Requested | Control Satisfied | Control Not Satisfied | Control Not Applicable | Remediation Not in Progress
Yes | No