## _PMO Remediation Export
(Do Not Modify) Risk Strategy Recommendation | (Do Not Modify) Row Checksum | (Do Not Modify) Modified On | Environment | VRAS Name | Vendor Security Risk Strategy Recommendation | Documentation Request | Risk Reduction Impact | Recommended Due Date | Remediation Strategy Accepted by Vendor | Contractually Agreed Upon Completion Date | Vendor Notes | Risk Strategy Status
117f896f-25c8-e811-a960-000d3a363daf | oaTgHwzWzWI0I/pYVfiSuRRbgxI9PedhesQhNcU5Ki1Rbgv5XFdoXcB8J7u67MO20d0rKOfAr7OqH+yL6nw6gA== | 2018-10-04 18:38 |  | VRAS for: Avera Health / PeriGen | CVR-SEC CERT-1.2 Obtain a third party audit (preferably SOC 2 Type 2 TSP at a minimum Security, Privacy and Confidentiality, HITRUST or ISO 27001) within 12-18 months specific to the application. A readiness report should be provided within 6 months. |  | High | 2020-06-30 | Yes
62ea7c54-25c8-e811-a960-000d3a363daf | fGvH/CClrWO7vZCaR5tCAl3Jfj5DkmWLcvyHxr7yKt1G6jehhUkWKFgaskDkcL3XJMUrLpCKjXv14Z4daHESpQ== | 2018-10-04 18:37 |  | VRAS for: Avera Health / PeriGen | CVR-SEC TEAM-1.1 Dedicate at least one (1) security person(s) to handle the primary day-to-day functions of a formal security program |  | Medium | 2019-12-31 | Yes
7d4aba62-25c8-e811-a960-000d3a363daf | CNtHVVFDti9+h+DL+01T7JfjAvSOLxdre1w1w6WgaC+ki4ojmgrGhyKWYfhOn5AEnyb/u8woWslBNZqUN05vcw== | 2018-10-04 18:37 |  | VRAS for: Avera Health / PeriGen | CVR-SEC LEADER-1.1 Appoint a Security Leader to maintain and oversight the security program of the organization |  | Medium | 2019-12-31 | Yes
9861b584-25c8-e811-a960-000d3a363daf | A9gGXapwIdvhzEgT0jyA1JSMDBtlfAH6m4uBLdOfxaSreX7nJNuMdZrZbSZuvqpDoyDJhzpE7jIARqw+7uY2iw== | 2018-10-04 18:38 |  | VRAS for: Avera Health / PeriGen | CVR-WEBSCAN-1.1 Update any and all outstanding patches to applications, domains and sub-domains, and provide evidence of the necessary updates |  | Low | 2019-03-31
bece0693-25c8-e811-a960-000d3a363daf | nvQsL9TUjEZwM2sLdl9o+zf+ZaqDsqnTfPmyHjQE6n5DcRM2q5jSi8RfzmCCG6MsgNqEn+u5Oo9wqtquW8bNMA== | 2018-10-04 18:38 |  | VRAS for: Avera Health / PeriGen | CVR-PRIVACY-1.2 Author and implement a public-facing privacy policy incorporating language specific to: Notice, Choice, Onward Transfer, Access, Security, Data Integrity, and Enforcement |  | Low | 2019-03-31
4f66446c-af5f-e911-a988-000d3a32401b | xRGf825bsTYb4BeMqiHG+SxdFo2yKwmNOdXfDONlljg9DKN+6m2Mx+3G3dj0NUZlTRraBZ3EheXbc4zbVGxhkw== | 2019-04-15 14:51 | General (On-Prem) | VRAS for: Avera Health / PeriGen | AT-3.1 Perform role-based security training for personnel with assigned security roles and responsibilities for the information system before access is granted | Provide Security Awareness and Training Policy and procedure Provide Evidence of annual security awareness and training results | Medium | 2019-09-30 | Yes
3d58fe6f-af5f-e911-a990-000d3a3241d4 | m5+OEXRdA6KMfWo8RIe9ck5ri15OM2sDK/B2yR8FAQiN1bp5L+3xB04RLomo+7aXzge5BW6+omfaOj5h7mHFVw== | 2019-04-15 14:51 | General (On-Prem) | VRAS for: Avera Health / PeriGen | AC-12.1 Configure the information system to terminate user sessions after predefined circumstances | Documented policy regarding session timeouts Print screen showing the configuration settings for session timeouts not associated with inactivity | Medium | 2019-09-30 | Yes
63006a6c-af5f-e911-a991-000d3a32476a | 6DKrWsepNZ3RRygWb4NMuMf7UwJ9ZSa8uzUsss/dByp4FJxOWB4NrgsuGXvhjdaYW3juyAbC1XVrThOPmNb3Xw== | 2019-04-15 14:51 | General (On-Prem) | VRAS for: Avera Health / PeriGen | IR-3.1 Conduct incident response tests | Provide completed Incident response testing, results and issues list | Medium | 2019-09-30
6001106f-af5f-e911-a998-000d3a324a3e | cb9Hfwv0GRbUuvVGnNQLnW/5ZHY/VfURVmWJfi8MNfHhEWhqAHj9h/sILJ/XY2pk2bLMorA+MyyGkHnBYGe+Fg== | 2019-04-15 14:51 | General (On-Prem) | VRAS for: Avera Health / PeriGen | IR-2.2 Provide Incident response training that is unique to the role of the individual | Provide evidence of completed incident response training. | Medium | 2019-09-30
7b899d6f-af5f-e911-a992-000d3a324ed7 | /q7rOmfMeBcbobpVz0BIZjhqxmxMjUyJixcg33lvMPpJhMhikd6rvktqYTPlmkNY54hHBcLqNBVOFXh2zktnBQ== | 2019-04-15 14:51 | General (On-Prem) | VRAS for: Avera Health / PeriGen | SA-5.4 Protect information system documentation as required and only distributed to authorized personnel |  | Low | 2019-09-30
7c899d6f-af5f-e911-a992-000d3a324ed7 | 8V9rgxC1sBfq5+tzl6GskgKCBSRFduu2wPoDtbbaLHtX2+kuzAtxR/9loQAsxgDCQ5rQlptX/w3t9uMwRspAog== | 2019-04-15 14:51 | General (On-Prem) | VRAS for: Avera Health / PeriGen | SA-1.1 Develop and implement formally documented policies and procedures for System and Services Acquisitions |  | Low | 2019-09-30
7d899d6f-af5f-e911-a992-000d3a324ed7 | oxyNw/sbaKM0Pc1jJuowjfy7WzzSR9l1Tz8WHRS5JUlPsV70jz2AoC+uOE2nljHNepupUzS51fvflk1vgvkSsw== | 2019-04-15 14:51 | General (On-Prem) | VRAS for: Avera Health / PeriGen | IA-5.9 Require token-based authentication for access to the information system | Single Sign On configuration settings. | Low | 2019-09-30
7e899d6f-af5f-e911-a992-000d3a324ed7 | xfc4ooDDvnEqWt237v1kULb4JrQo3WeN+Jj1b+7F6pYBttsLUY06crVwkgEIyAR98x6LICd9Ie2aUQ+TZ0eDtA== | 2019-04-15 14:51 | General (On-Prem) | VRAS for: Avera Health / PeriGen | SC-10.1 Configure the information system to terminate network connections associated with a communication session at the end of the session or after no longer than 30 minutes of inactivity |  | Low | 2019-09-30
7f899d6f-af5f-e911-a992-000d3a324ed7 | IJECrqbyeNvQxfOiey1+6q/LSVmIYYA4M++r8bpYpkjjdQs9Sc+PVv3jE/1a/38Q9d6AtIpBciyRLNc6QeySmQ== | 2019-04-15 14:51 | General (On-Prem) | VRAS for: Avera Health / PeriGen | SC-23.1 Implement controls for protecting the authenticity of communication sessions |  | Low | 2019-09-30
80899d6f-af5f-e911-a992-000d3a324ed7 | 3C/5LwkxJyv/3y6qL1dopD8fHGM9jvKqUXJl2WPZQ6AOSeLJllCnAxeDPzLIceKXkx2YEUlREIBcfmnASV/YzQ== | 2019-04-15 14:51 | General (On-Prem) | VRAS for: Avera Health / PeriGen | AC-8.1 Implement system use notifications that provide privacy and security notices before granting access |  | Low | 2019-09-30
81899d6f-af5f-e911-a992-000d3a324ed7 | qI+VeKlDKJlEiJ048SAdFnSBQKrvfuSllv5XneiIMNBr9/0ey1aCI1wHAkWI10eJYC+7O7hVoQZQHm+gM2lHPg== | 2019-04-15 14:51 | General (On-Prem) | VRAS for: Avera Health / PeriGen | SA-11.1 Require the developer of the information system to create and implement a security assessment plan, perform tests/evaluations and produce evidence of the execution of the security assessment plan | Please provide the developer's security assessment plan and copies of tests/evaluations that demostrates of the execution of the security assessment plan? | Medium | 2019-09-30 | Yes
82899d6f-af5f-e911-a992-000d3a324ed7 | qmilSVuz9nnD/+60XWbyk1k89wRLsnlgkwewkpNi+WxNQ7OXSHvQn8W3SWshofvDcmWGJY2c2V2l5bcAXfSSfQ== | 2019-04-15 14:51 | General (On-Prem) | VRAS for: Avera Health / PeriGen | AU-12.1 Configure the information system with the capability to select which auditable events are captured in the audit log |  | Low | 2019-09-30
83899d6f-af5f-e911-a992-000d3a324ed7 | 6kopEWLZeKBwY4laYnYvlPKOhAdACWqHcnDMP3b9MLmuyJ6bo83WtAnRSdGbNRf53Hgl0nDGP/cIh1dRfXnIqA== | 2019-04-15 14:51 | General (On-Prem) | VRAS for: Avera Health / PeriGen | IA-4.2 Configure the information system to prevent reuse of user or device identifiers |  | Low | 2019-09-30
84899d6f-af5f-e911-a992-000d3a324ed7 | tP6+T8anJzNDxkdTFmYhJTGW/LzqsPThk0ZPEVJCvjcFyNDe0a1om6QpcpI8wknuX5l7gr0eJsAp+D8glr68eQ== | 2019-04-15 14:51 | General (On-Prem) | VRAS for: Avera Health / PeriGen | PS-3.2 Implement processes to re-screen individuals with access to the information system | Provide policy regarding Hiring/Onboarding Requirements Please provide redacted copies of screening reports for the past 6 months | Low | 2019-09-30
85899d6f-af5f-e911-a992-000d3a324ed7 | MqrvX4QpSPauER1eP7tH0dwB5Z2qtBB5oXSnV2r19TE4P0iDPt20Z7dcyrD1dBHR/Vbe/iC9zzQE/uGItml0vA== | 2019-04-15 14:51 | General (On-Prem) | VRAS for: Avera Health / PeriGen | IR-3.2 Analyze incident response tests | Provide completed Incident response testing, results and issues list | Medium | 2019-09-30
86899d6f-af5f-e911-a992-000d3a324ed7 | NyVKF/Z++zCeuKfgmkEH5ZlSjS4TqgszFNAXixqPbn8XwIpB+Bcp2czDFSKp7Avm6OeDeIfvc/Ndae0K3umJ5A== | 2019-04-15 14:51 | General (On-Prem) | VRAS for: Avera Health / PeriGen | AC-10.1 Configure the system to limit the number of concurrent sessions for users |  | Low | 2019-09-30
87899d6f-af5f-e911-a992-000d3a324ed7 | itjawHqlRYXfPdiYlGgEAzHecL62Db4hNwu6cIFoYhxo9cGrZojGEMDh8Z3CEz6PYkuwms8dmWBg49TxOm5p1Q== | 2019-04-15 14:51 | General (On-Prem) | VRAS for: Avera Health / PeriGen | SI-1.1 Develop and implement policies and procedures for System and Information Integrity |  | Low | 2019-09-30
89899d6f-af5f-e911-a992-000d3a324ed7 | liaHDvSz8NUl7+t0y1IY2zv/1WBTqh5rS668n0FPQe2yLFJ9XF1Y4dhx9inCUab2AKlMTYfP2LTBDLDVk/Haqg== | 2019-04-15 14:51 | General (On-Prem) | VRAS for: Avera Health / PeriGen | AC-9.1 Configure the system to display the previous date and time of a user's last login |  | Low | 2019-09-30
8a899d6f-af5f-e911-a992-000d3a324ed7 | rGXZ72tZx+HYYQtcj/WloQw0ZY/rcynjiA2lvRKUIT9ySaHW8VjgyBaqUzyEvaIcVr5pm5dIXm8ixB4xH1fXzg== | 2019-04-15 14:51 | General (On-Prem) | VRAS for: Avera Health / PeriGen | PS-5.1 Implement appropriate transfer procedures for those with access to the information system | Provide Transfer policy, procedure, process. | Low | 2019-09-30
8b899d6f-af5f-e911-a992-000d3a324ed7 | 8phvSrjx6xwvuPcE+bWk45SkJeyL8DTkBykuuMK02cJ4TSwuTebgc4fNhEA980PpseCSpwsisi8wkI2iSBx/tA== | 2019-04-15 14:51 | General (On-Prem) | VRAS for: Avera Health / PeriGen | CM-12.2 Require the Organization to develop and implement policies that define the timing for applying patches to the information system | Provide Patch Management Policy/Procedure Provide Change control Policy procedure Provide evidence of implemented patches for the prior three months | Low | 2019-09-30
8c899d6f-af5f-e911-a992-000d3a324ed7 | oxXc+wltvJuxA/TqsLE1lRhoK/K/28D8oaogTgn0Llnu7PbCX8m76way0yysYOSdWqjKdio4TGqFKx3Kfy5jGA== | 2019-04-15 14:51 | General (On-Prem) | VRAS for: Avera Health / PeriGen | PS-2.1 Assign risk designations to all positions |  | Low | 2019-09-30
8d899d6f-af5f-e911-a992-000d3a324ed7 | iPk5/kuS4QNNeoJc5vYTA9yWwN6/hcRJYwGmxJeBJmNv629pZ2bavluzg27+Pr7O1Ku+6yXPP2t6B4wxlflSHg== | 2019-04-15 14:51 | General (On-Prem) | VRAS for: Avera Health / PeriGen | PS-2.3 Implement processes for reviewing and revising position risk designations at least every three years |  | Low | 2019-09-30
8e899d6f-af5f-e911-a992-000d3a324ed7 | IQUUdFE8Aa0PIzZ5TmHEUDfqVo3zPpklEMATODekSjtsdXp+zL3cjGra+1XayJa35U98MBkGjLx4SeYbB0pkRg== | 2019-04-15 14:51 | General (On-Prem) | VRAS for: Avera Health / PeriGen | SC-1.1 Develop and implement policies and procedures for System and Communications Protection |  | Low | 2019-09-30
8f899d6f-af5f-e911-a992-000d3a324ed7 | eERGrHHO4y8EcjEIxqo7P42p+TPr+Y6ADPzes2iYSsLWEXqd9C22Naqb5uiU8iqbd3XWLRFiwRoIVQrCsgFk/A== | 2019-04-15 14:51 | General (On-Prem) | VRAS for: Avera Health / PeriGen | IA-2.1 Implement multifactor authentication for privileged and non-privileged access | Provide supporting evidence to substantiate multi-factor authentication is implemented. | Low | 2019-09-30
90899d6f-af5f-e911-a992-000d3a324ed7 | Y4haxpfGFgIbNrNV1ccDz19q4PmxUktJfaeDGz46KVYUgi+tgE7bkmr5lSUNzMz7PwE48I90w4dDouMHJBoXvA== | 2019-04-15 14:51 | General (On-Prem) | VRAS for: Avera Health / PeriGen | SA-5.2 Develop user documentation that describes: 1 User-accessible security functions/mechanisms and how to effectively use those security functions/mechanisms; 2 Methods for user interaction, which enables individuals to use the system, component, or service in a more secure manner; and 3 User responsibilities in maintaining the security of the system, component, or service |  | Low | 2019-09-30

## Sheet1
Questions/clarifications
| CVR-SEC CERT-1.2 Obtain a third party audit (preferably SOC 2 Type 2 TSP at a minimum Security, Privacy and Confidentiality, HITRUST or ISO 27001) within 12-18 months specific to the application. A readiness report should be provided within 6 months. | This is primarily for the application we provide correct?
| CVR-SEC TEAM-1.1 Dedicate at least one (1) security person(s) to handle the primary day-to-day functions of a formal security program | Being a relatively small development shop, we don’t have 100% dedicated resource divide different responsabilities among seveal team members as needed. For example, I am the "security Leader" in the organization among other responsibilities. I have multiple delegates in the development and operations team to address specific security issues. Does that satisfies the question?
CVR-SEC LEADER-1.1 Appoint a Security Leader to maintain and oversight the security program of the organization
General (On-Prem) | AT-3.1 Perform role-based security training for personnel with assigned security roles and responsibilities for the information system before access is granted | We do have that and I will forward the policy and evidence
General (On-Prem) | AC-12.1 Configure the information system to terminate user sessions after predefined circumstances | We do have that and I will forward the policy
General (On-Prem) | IR-3.1 Conduct incident response tests | Are all IR related questions relate to PeriGen internal IT procedures OR out support IR relevant to the product installed at the customer site. Reminder, we don’t transmit, manage any aspect of customer PHI on our corporate infrastructure.
General (On-Prem) | IR-2.2 Provide Incident response training that is unique to the role of the individual
General (On-Prem) | SA-11.1 Require the developer of the information system to create and implement a security assessment plan, perform tests/evaluations and produce evidence of the execution of the security assessment plan | We do have a plan for this.
General (On-Prem) | IR-3.2 Analyze incident response tests

## Sheet2
Bed Name | Wallplate | Playback Strip
SP-LDR3 | Primary | 1060941KKLates
SP-LDR1 | Secondary
SV-LDR2 | Primary | 1060941KKLates
SP-LDR2 | Secondary
SP-LDR4 | Primary | 5139530UTDec
SP-LDR3 | Secondary
SR-TR1 | Primary | 5139530UTDec
SP-LDR4 | Secondary
SR-LDR5 | Primary | 620878NmlMxdDclc
SP-LDR5 | Secondary
SP-LDR5 | Primary | Continuous PulseOX
SR-LDR1 | Secondary
SR-LDR3 | Primary | G120877Normal
SR-LDR2 | Secondary
SR-LDR1 | Primary | Mostly Normal
SR-LDR3 | Secondary
SV-LDR4 | Primary | Mostly Normal
SR-LDR4 | Secondary
SP-LDR1 | Primary | Normal
SR-LDR5 | Secondary
SP-LDR2 | Primary | Normal and Decel
SR-TR1 | Secondary
SR-LDR4 | Primary | Normal and Decel
SV-LDR1 | Secondary
SR-LDR2 | Primary | NormalTracing_NormalVS
SV-LDR2 | Secondary
SV-LDR3 | Primary | NormalTracing_NormalVS
SV-LDR3 | Secondary
SV-LDR1 | Primary | Real5_NormalVS
SV-LDR4 | Secondary

## hiddenSheet (hidden)
ct_vrasriskstrategyrecommendation:tx+WhblYv27x1ss+Vy7j9eizxcXEb1Ys6y2CXAmrPHUsvWEcQkiCzMrqruXn6gcOt8aILk4zhpIooCkYBK2Ptg==:ct_vrasriskstrategyrecommendationid=%28Do%20Not%20Modify%29%20Risk%20Strategy%20Recommendation&checksumLogicalName=%28Do%20Not%20Modify%29%20Row%20Checksum&modifiedon=%28Do%20Not%20Modify%29%20Modified%20On&ct_environment=Environment&ct_vrasid=VRAS%20Name&ct_vendorsecurityriskstrategyrecommendation=Vendor%20Security%20Risk%20Strategy%20Recommendation&ct_documentationrequest=Documentation%20Request&ct_riskreductionimpact=Risk%20Reduction%20Impact&ct_recommendedduedt=Recommended%20Due%20Date&ct_remediationstrategyacceptedbyvendor=Remediation%20Strategy%20Accepted%20by%20Vendor&ct_contractuallyagreeduponcompletiondate=Contractually%20Agreed%20Upon%20Completion%20Date&ct_vendornotes=Vendor%20Notes&ct_newriskstrategystatus=Risk%20Strategy%20Status
Yes | No
Client Accepted Risk | Control Satisfied | Control Not Satisfied | Control Not Applicable | Accepted | Not Accepted | Sent to Vendor | Evidence Requested