## Pericalm
| Corrective Action Plan: | Pericalm |  |  | Tracking 9 Vulnerabilities
| Overall Risk Rating: | 5
| Date Risk Assessment Completed: | 2022-10-10
| Findings | Recommendations | Corrective Actions | Compensating Controls | Targeted Implementation Date | Actual Implemented Date | Risk Score | Estimated Resources (Capital Expense, and Hours) | Possible End User Impact(s) | PeriGen comments
1 | Pericalm runs and houses sensitive data onsite on Microsoft Windows Server 2012 and Microsoft SQL Server 2014 | Purchase extended support for Microsoft SQL 2014 or upgrade to newer version; plan for upgrade of Microsoft 2012 server EOL 10/2023 |  |  |  |  | 6 |  |  | Primarily, data is stored in the object oriented DB (Objectivity/DB). This OODBMS is bundled with the application. The SQL database is only used as an intermediary between the HL7 interface and the PeriCALM application. As such, only some limited PHI is stored in SQL, namely, MRN, Account# and clinical observations. No patient names are stored here. Customer can upgrade SQL to SQL 2016. If that decision is made, it has to be first implemented in the test environment. Note that the Objectivity/DB as a company is no longer in business which was the primary trigger for the EOL (end of life) notice for the PeriCALM platform which is to be replaced by the PeriWatch platform. A separate notice to that effect was sent to all PeriCALM customer in Jan. 2024 and a demonstration of the PeriWatch Surveillance platform was performed to motivate customers to migrate asap.
2 | There is no technical control preventing users from copying large amounts of confidential information from within the application database to some type of portable media or directly faxing it or emailing it outside of the organization | Implement technical controls to prevent data exfiltration (AD group policy to control USB use; daily monitoring of Exchange email archive solution) |  |  |  |  | 6 |  |  | Agreed; such technical controls would provide an additional layer of security
3 | Unsure on SSL, SFTP controls for all interfaces / exchanges has not been identified | Document and validate all Interfaces / Exchanges and protocols in place |  |  |  |  | 5 |  |  | TCP/IP ports 91, 92, 7802, 7803 PODI interface to PeriCALM Patterns EHR interface to EMR system Corepoint interface for ADT MSMQ interface between workstations and server LDAP or LDAPS may be in use for Active Directory authentication, depending on configuration
4 | Vendor has approx. 10 support team members that can access super user privileged account “periadmin”. This ID is set to never expire and never change | Restrict 1) super user access to only those who actually require it to be able to create or modify user accounts (security access) 2) Create a “Break the Glass” policy and procedure to grant access to ePHI during emergencies |  |  |  |  | 5 |  |  | Vendor access is via SecureLink which requires individual login; once logged in, admin access is through shared periadmin account as stated. Customer to define internal policy
5 | Pericalm stores PHI and SSNs; the database is not encrypted | If the database cannot be encrypted, document compensating controls that protect data at rest |  |  |  |  | 5 |  |  | PeriCALM does store PHI but no SSNs. As mentioned above, this data is primarily stored on Objectivity/DB OODBMS which is managed by PeriGen. Data is not explicitly encrypted but the recommendation is to encrypt the storage volume that the database is hosted on which is on the application server.
6 | User access rights are not periodically reviewed by application owners or managers to ensure they are appropriate, this only happens upon request | Create policy and procedure to state that managers or application owners are required to review user access on a periodic basis to determine if employee access is appropriate |  |  |  |  | 4 |  |  | Customer to define internal policy
7 | It is not certain whether or not each department has these downtime procedures in a written format and in an easily accessible location in case of a downtime event | Validate whether or not each department has these downtime procedures in a written format and in an easily accessible location in case of a downtime event |  |  |  |  | 4 |  |  | Agreed; customer should validate downtime procedures
8 | Restoration procedures for IT are not documented in the Disaster Recovery Plan | Document a disaster plan for Pericalm that meets organizational requirements; periodically test and update the plan |  |  |  |  | 4 |  |  | Agreed; customer should document and test disaster recovery plan
9 | There is no documented audit policy/strategy. Audit logs are reviewed only upon request “as needed” using Pericalms Audit tool | Document an audit policy/strategy |  |  |  |  | 4 |  |  | Customer to define internal policy
| Risk Score Legend: |  |  |  | Last reviewed on:
Attendees: