## _PMO Remediation Export
(Do Not Modify) Risk Strategy Recommendation | (Do Not Modify) Row Checksum | (Do Not Modify) Modified On | Environment | VRAS Name | Vendor Security Risk Strategy Recommendation | Documentation Request | Risk Reduction Impact | Recommended Due Date | Remediation Strategy Accepted by Vendor | Contractually Agreed Upon Completion Date | Vendor Notes | Risk Strategy Status
997b14b3-0caf-e911-a994-000d3a32401b | ujqsImz5n+ahPbdM7t4D/d6NKxzBOGDE/mS1UG09lyNkPDX98JJ0zsebkAhDGeN8QGhCTL9A9ZuugoYUi5L8Yg== | 2019-07-25 18:48 | General | VRAS for: The Christ Hospital / PeriGen | CVR-SEC LEADER-1.1 Appoint a Security Leader to maintain and oversight the security program of the organization |  | Medium | 2020-09-30 | No |  | Bruno Bendavid is the appointed leader | sent to vendor
9a7b14b3-0caf-e911-a994-000d3a32401b | pdSuzKLO3ubPqkUJm+OlrhiD1WT8G0vSi2NGbYziD7OwXivc4wI1QExXm4b1sdlm8do2LGSwxdyWvlPBY+nbVQ== | 2019-07-25 18:48 | General | VRAS for: The Christ Hospital / PeriGen | CVR-SEC CERT-1.2 Obtain a third-party audit (preferably SOC 2 Type 2 TSP at a minimum Security, Privacy and Confidentiality, HITRUST or ISO 27001) within 12-18 months specific to the application. A readiness report should be provided within 6 months. |  | Medium | 2021-03-31 | Yes |  |  | sent to vendor
9b7b14b3-0caf-e911-a994-000d3a32401b | UHxsoylQpFF5sMyj6Zw8u3febbJm59kl3zmu2GwVSjEVgZuoxIZw4FwWgBO32AlGeLutyLA2fhLirxtzXTrgxQ== | 2019-07-25 18:48 | General | VRAS for: The Christ Hospital / PeriGen | CVR-SEC TEAM-1.1 Dedicate at least one (1) security person(s) to handle the primary day-to-day functions of a formal security program |  | Medium | 2020-09-30 | No |  | Day to day issues are address by our ticketing system and treated by severity, how wide spread the problem is and any patient safety concerns. Actions are derived based on analysis according to our internal QMS procedures. As such, security issues are "owned" by the development team | sent to vendor
4bb5b2b2-0caf-e911-a99e-000d3a324f4c | hG6y6kuBL9SAHcYoHTR3N7eBrLohpWZVwmP080huTCO5FWU3hBxxNpkE5Sr5B3M7PSwvJfWudHO/Rwk4DDhBcg== | 2019-07-25 18:48 | General | VRAS for: The Christ Hospital / PeriGen | CVR-WEBSCAN-1.1 Update any and all outstanding patches to applications, domains and sub-domains, and provide evidence of the necessary updates |  | Low | 2019-12-31 | Yes |  | Need clarity on the meaning of F5. assuming I correctly understand the Hospital based systems are patched regularly by customers. Corporate systems are updated regularly by domain controller policies. | sent to vendor
0620b1b8-0caf-e911-a99e-000d3a324f4c | fwPCq6W8ySxM0WDxuBDaqs9ixQXO5k+AHy+D6khHJLrZnbOop6jHQSf4wt6QaB1hD9fvQtP9CdjcxZhsr2ohXQ== | 2019-07-25 18:48 | General | VRAS for: The Christ Hospital / PeriGen | CVR-PRIVACY-1.1 Update the public-facing privacy policy to include appropriate language specific to: Notice, Choice, Onward Transfer, Access, Security, Data Integrity, and Enforcement |  | Low | 2019-12-31 | No |  | Please further clarify | sent to vendor
2c192684-9cdb-e911-a99e-000d3a32401b | 5LzPhq9L2PPJ/AQ+gTe3fsdX6UstOlw8HopyWammFO8f5x8NYWvtxyjLA5a3baPivG7xFAncdSgz39AmG2xVLg== | 2019-09-20 11:48 | General (Unknown) (On-Prem) | VRAS for: The Christ Hospital / PeriGen | CA-5.1 Use previous security assessment results to mitigate identified risks. | Provide doucmentation that demostrates corrective actions plans are created to remediate risks identified from previous assessments. | Medium | 2019-12-31 | No |  |  | sent to vendor
2d192684-9cdb-e911-a99e-000d3a32401b | kydZ25AHYjbCSzd9rmDd96RZVBc7Jxb0MIFoHb9UVTHtpFtNp1BMNwCWPOSecpxDZHeGCoQdxFabKGmEupUX1g== | 2019-09-20 11:48 | General (Unknown) (On-Prem) | VRAS for: The Christ Hospital / PeriGen | PS-2.1 Assign risk designations to all positions. |  | Low | 2019-12-31 | No |  | March 31, 2020 | sent to vendor
2e192684-9cdb-e911-a99e-000d3a32401b | PalTUgtEUtMDv2ihdQVmCcCwS+wnw8l3mFUe2fpk097td6zhRfyqFzLoE5DmmE8/SNTLHpJxbji0v+RZsPJ+4Q== | 2019-09-20 11:48 | General (Unknown) (On-Prem) | VRAS for: The Christ Hospital / PeriGen | CM-12.2 Require the organization to develop and implement policies that define the timing for applying patches to the information system. | Provide Patch Management Policy/Procedure Provide Change control Policy procedure Provide evidence of implemented patches for the prior three months | Low | 2019-12-31 | Yes |  | These are being implemented regularly. | sent to vendor
2f192684-9cdb-e911-a99e-000d3a32401b | bScH4Wg+M4jrztQRw/P+3ZNb/jkc8Q0TbROc3fkHRdderHv/megjiOxEPEyHOaNLx+Zk9M+wgsxZ1TGmYG9UVQ== | 2019-09-20 11:48 | General (Unknown) (On-Prem) | VRAS for: The Christ Hospital / PeriGen | AU-12.1 Configure the information system with the capability to select which auditable events are captured in the audit log. |  | Low | 2019-12-31 | No |  | The system provides audits for ALL captured/written data. There is no option to select/remove elements. Perhps the answer to AU-12.1 must be revised to YES | sent to vendor
30192684-9cdb-e911-a99e-000d3a32401b | rpV085ZI10Uqp84DKFL5wY0W6Htv3swB7ydIP5tI/TsEOIUgflr3H8m83oKiE5dM8xzlTjl1i+UTJTLXW9haZA== | 2019-09-20 11:48 | General (Unknown) (On-Prem) | VRAS for: The Christ Hospital / PeriGen | AC-10.1 Configure the system to limit the number of concurrent sessions for users. | 1) Screenshot of Active Directory Group Policy (GPO) Settings 2) Screenshot of Active Directory Configuration | Low | 2019-12-31 | No |  | Customer configurable by the customer. PeriGen does not control customer AD policies. | sent to vendor
31192684-9cdb-e911-a99e-000d3a32401b | t9A4LKXAJ8euPf8bAWxB39cJnwfduqsIFef6ra2sIFrwm+GmifignAXJUsdk89EggN4IF+y2ONwDQTpHi9cbqA== | 2019-09-20 11:48 | General (Unknown) (On-Prem) | VRAS for: The Christ Hospital / PeriGen | IR-3.1 Conduct incident response tests. | Provide completed Incident response testing, results and issues list | Medium | 2019-12-31 | No |  | Not before March 31 2020 | sent to vendor
32192684-9cdb-e911-a99e-000d3a32401b | 7sOgWflLoPDTnvxh2df3WhbtukqbkG38ZzVhDn33eXlHfvHmRe3IrZRmxa2yK6QC3ZD1QcFNh+Qlj0sIy3HqvQ== | 2019-09-20 11:48 | General (Unknown) (On-Prem) | VRAS for: The Christ Hospital / PeriGen | MP-7.1 Require the organization to implement restrictions on the types of storage media that can connect to the information system. |  | Low | 2019-12-31 | No |  | PeriGen does not store PHI. Annual training and internal policies cover good practices regarding storage media and AV end-point protection are configured to scan connected external media | sent to vendor
33192684-9cdb-e911-a99e-000d3a32401b | 3odPD0xhhwCFHkc5jagZJJAPx0LPKr6N/pGHt4NsvlXjZzFJp7t08cPqpieJ7Hxmx89PHzMt6XZnsIUpRomr0g== | 2019-09-20 11:48 | General (Unknown) (On-Prem) | VRAS for: The Christ Hospital / PeriGen | AC-20.1 Establish terms and conditions for trust relationships with external environments to define acceptable processing of organizational information in those environments. | Policy/procedure regarding third party connection agreements in support of information flow control and RBAC. | Low | 2019-12-31 | No |  | No such connection between PeriGen and external networks are in effect or needed. | sent to vendor
34192684-9cdb-e911-a99e-000d3a32401b | PtwQXgZwqsw9fw77d5CDTsyo7iRXbThx+f1DvzJpQE5PkR4VCc3uAx9JWoVRNvDdK1glHKlblcwNH02FG5Xleg== | 2019-09-20 11:48 | General (Unknown) (On-Prem) | VRAS for: The Christ Hospital / PeriGen | IA-1.2 Develop and implement formally documented policies and procedures for Identification and Authentication. |  | Low | 2019-12-31 |  |  | Covered in the policy I have attached in September. | sent to vendor
35192684-9cdb-e911-a99e-000d3a32401b | 0piYO4SLl25VlxquZGGKNtjUbUnjuK8woT6qR57p+v3r9OvFBNUh9JJE6G7vjycR1isFZxT7Uk8smUa7DnUgYA== | 2019-09-20 11:48 | General (Unknown) (On-Prem) | VRAS for: The Christ Hospital / PeriGen | IA-4.2 Configure the information system to prevent reuse of user or device identifiers. |  | Low | 2019-12-31 | Yes |  | Not sure why this answer was a "NO", if I understand correctly, workstations, devices attached to the system or even users must be unique and cannot be duplicated. This is the case in the PeriGen system. If so, we need to change the IA-4.2 answer to YES | sent to vendor
37192684-9cdb-e911-a99e-000d3a32401b | J789/3LOVubNc2CO0agmXxgLbliPlBwTQ691K63IvtzE30aCWGA/yM+pEiJ/id+EMz/sXBUw+aesR9N9/4VKpA== | 2019-09-20 11:48 | General (Unknown) (On-Prem) | VRAS for: The Christ Hospital / PeriGen | AC-9.1 Configure the system to display the previous date and time of a user's last login. |  | Low | 2019-12-31 | No |  | Data available in audit logs. Clinical users will not approve a mechnism that slows doen their authentication process. | sent to vendor
38192684-9cdb-e911-a99e-000d3a32401b | RuDp7QbS570L+rjAClelMboGCf0JzMvEcl9DsMCLEcvk042txEZNxzQ7IsuO0ZZOPqhBIGAG1klSVCYRVM4n6w== | 2019-09-20 11:48 | General (Unknown) (On-Prem) | VRAS for: The Christ Hospital / PeriGen | CP-7.1 Implement an alternate processing site to permit the resumption of the information system operations for essential missions and business functions. |  | Low | 2019-12-31 | No |  | No required for the size of the company. Essential business operation can be easily resumed being on Office365 and Microsoft Online Team Services (VSTS) and accessing customer sites using customer approved cloud-based secure comminucation service. This is also covered by the policy sent in Sept. | sent to vendor
39192684-9cdb-e911-a99e-000d3a32401b | RHz3w6mllpep8m7Cjg/yuGQGYuJQh9D2RdQ0bsyOXihWFYAxavX+4kBej7g9gYd0Z4zx5l96kmpqVP4ujgmSjQ== | 2019-09-20 11:48 | General (Unknown) (On-Prem) | VRAS for: The Christ Hospital / PeriGen | CA-9.1 Develop documentation on what information is communicated with the device or component used with this system. | Please provide documentation on what information is communicated with the external device or components, how information is transferred, and how the data is secured | Low | 2019-12-31 |  |  | We do communicate with fetal monitors | sent to vendor
3a192684-9cdb-e911-a99e-000d3a32401b | inaUBNWuYMGMMMXA+9c3fziJ/mrbXFWU2vYGZM52QhcE+wwt+sjZ24uHz7zwMLt1wTAjyZOTu08L8jSkx7Mm4g== | 2019-09-20 11:48 | General (Unknown) (On-Prem) | VRAS for: The Christ Hospital / PeriGen | SA-11.1 Require the developer of the information system to create and implement a security assessment plan, perform tests/evaluations and produce evidence of the execution of the security assessment plan. | Please provide the developer's security assessment plan and copies of tests/evaluations that demostrates of the execution of the security assessment plan? | Medium | 2019-12-31 |  |  |  | sent to vendor
3b192684-9cdb-e911-a99e-000d3a32401b | nJ4N6r+rse91nQBLxarcXwFxi6aFaZETWhzJ+JQYTOHNfhKhLHE+mJ8oXXA/QNG/8j1EjB9ZmxOIlIsw4ETdbw== | 2019-09-20 11:48 | General (Unknown) (On-Prem) | VRAS for: The Christ Hospital / PeriGen | IR-3.2 Analyze incident response tests. | Provide completed Incident response testing, results and issues list | Medium | 2019-12-31 |  |  |  | sent to vendor
3c192684-9cdb-e911-a99e-000d3a32401b | CVbeLhdfD3hMpCLVA1zCxSjHYLP9q4ShDhrqkOXjv7lUhgCkQybkSYdNwHaG+fb7BbgyPW0S4VADETL5ZFAaMg== | 2019-09-20 11:48 | General (Unknown) (On-Prem) | VRAS for: The Christ Hospital / PeriGen | AC-8.1 Implement system use notifications that provide privacy and security notices before granting access. |  | Low | 2019-12-31 |  |  |  | sent to vendor
3d192684-9cdb-e911-a99e-000d3a32401b | u5y4TTdPRZ5o0yXK8nvDw6PuNKxEdg8Qtwkcz/1nZ1kf+NwIb/hIq/hbZd++Vad6d2L0RSts2OFS2+zAmeVetQ== | 2019-09-20 11:48 | General (Unknown) (On-Prem) | VRAS for: The Christ Hospital / PeriGen | IR-2.2 Provide Incident response training that is unique to the role of the individual. | Provide evidence of completed incident response training. | Medium | 2019-12-31 |  |  |  | sent to vendor
3e192684-9cdb-e911-a99e-000d3a32401b | jhh/5N7U5+7m0kzzfWEuT33kNATEsZLRGfO5Gf0Yl2ilrDVcebkKXx6sipXpWGRzHmvVV1/LjA/YwH1ReyPEZQ== | 2019-09-20 11:48 | General (Unknown) (On-Prem) | VRAS for: The Christ Hospital / PeriGen | CP-4.1 Implement a Contingency Plan test and/or exercise to determine the plan’s effectiveness and review the contingency plan test results to initiate any needed corrective actions. |  | Low | 2019-12-31 |  |  |  | sent to vendor
41192684-9cdb-e911-a99e-000d3a32401b | +zSqc3Y3nImiNHf2aqO8PgRSLp7xu1esbeQdR3PehslBy/SbdmBmgfmC4k0iFgqJiND4hA5d4M8QD3GYvN+Vuw== | 2019-09-20 11:48 | General (Unknown) (On-Prem) | VRAS for: The Christ Hospital / PeriGen | IA-5.9 Require token-based authentication for access to the information system. | Single Sign On configuration settings. | Low | 2019-12-31 |  |  |  | sent to vendor
45192684-9cdb-e911-a99e-000d3a32401b | xn5U/0p32DDtN8JKCyMcaatjZMlo6rQMczwywVtGxNlp0a0HVR09+zNFDwVba57CdMbLd+jP5/9xDUqyRB9gRQ== | 2019-09-20 11:48 | General (Unknown) (On-Prem) | VRAS for: The Christ Hospital / PeriGen | IA-2.1 Implement multi-factor authentication for privileged and non-privileged access. | Provide supporting evidence to substantiate multi-factor authentication is implemented. | Low | 2019-12-31 |  |  |  | sent to vendor
56192684-9cdb-e911-a99e-000d3a32401b | LgPXwXm3BLiqH4V2qRD0FeivUeMXds+Xzwg4qcoQjBcipsmwHKf4JeYt8/ALfRM3I7hO9FEmXAwZdsGFc8VEnw== | 2019-09-20 11:48 | General (Unknown) (On-Prem) | VRAS for: The Christ Hospital / PeriGen | PS-3.2 Implement processes to re-screen individuals with access to the information system. | Provide policy regarding Hiring/Onboarding Requirements Please provide redacted copies of screening reports for the past 6 months | Low | 2019-12-31 |  |  |  | sent to vendor
5d192684-9cdb-e911-a99e-000d3a32401b | 0t1L5/R4iEieTsPMzTT1MkEXXfB98w/zIn8RPM7hGHSaIFYRzlm1qFuPdv6XfdjBNJX8fJoeAVdjtHvR5bvj7A== | 2019-09-20 11:48 | General (Unknown) (On-Prem) | VRAS for: The Christ Hospital / PeriGen | PS-2.3 Implement processes for reviewing and revising position risk designations at least every three years. |  | Low | 2019-12-31 |  |  |  | sent to vendor
0f32fb83-9cdb-e911-a9a5-000d3a3241d4 | 9x8W7U3Nx1FtV8Y5sCg4KVeQDxRO9K0Fk0n2XSkHKsulVnM6CDDEGDTtq2kb8ApmnKSXd9LPDbwqyqnjBFA/Dg== | 2019-09-20 11:48 | General (Unknown) (On-Prem) | VRAS for: The Christ Hospital / PeriGen | AC-12.1 Configure the information system to terminate user sessions after predefined circumstances. | Documented policy regarding session timeouts Print screen showing the configuration settings for session timeouts not associated with inactivity | Medium | 2019-12-31 |  |  |  | sent to vendor
9d515b85-9cdb-e911-a9a5-000d3a32476a | StPf9wmeoqJpbSRi8t7k5uxhNJof/L6OOpDZlkCOiL6S5m/AMQq6GPqEa7xrVIAyBd/SKauRohUOFwvMhPwrpQ== | 2019-09-20 11:48 | General (Unknown) (On-Prem) | VRAS for: The Christ Hospital / PeriGen | AT-1.1 Develop and formally document procedures for security awareness and training. |  | Medium | 2019-12-31 |  |  |  | sent to vendor
586b5781-9cdb-e911-a9a6-000d3a324a3e | OLjjXr9BIYOOZNp/fqHcQA+T5KivRKRTzbxRM2yuJtCLQra/GCEKGAXZK5FSzpsSlUunprvFWBSgObCZubCWrA== | 2019-09-20 11:48 | General (Unknown) (On-Prem) | VRAS for: The Christ Hospital / PeriGen | SA-12.1 Employ a Vendor Risk Management function within the information security strategy to protect against supply chain threats to the information system. | Policies for acquiring third party services that will connect to the entity's network, data, software, etc. Procedures for acquiring third party services that will connect to the entity's network, data, software, etc. Vendor assessment questionnaire; if questionnaires are not utilized please provide the documentation which identifies information security risks or lack thereof posed by a vendor with access to scoped systems. Vendor due diligence protocols List of all sub-contract companies/individuals with access to client's data. Listing of all new vendors within the previous 3 months that have an association to IT (entity's network, data, software, etc.) along with completed procedures for approval/acceptance into your environment | High | 2019-12-31 |  |  |  | sent to vendor
6c6b5781-9cdb-e911-a9a6-000d3a324a3e | keoaOMFpag7tXQwJqoV8oOW1lzZKDwjhjWHAxOKDNQySRuKCWjfsRcq0VOkcWONUYQ/jvmL4gpAJVqCYUQHmEg== | 2019-09-20 11:48 | General (Unknown) (On-Prem) | VRAS for: The Christ Hospital / PeriGen | PS-5.1 Implement appropriate transfer procedures for those with access to the information system. | Provide Transfer policy, procedure, process. | Low | 2019-12-31 |  |  |  | sent to vendor
cac08b7f-9cdb-e911-a9a9-000d3a324ed7 | nG/voY4o80e3ISs/iRv9fUACHDZBupvcltFyIuj4lIpfXRFnj9DI7MkSDr+OdzjhgZl90LAkesr7J9Nd51/+xw== | 2019-09-20 11:48 | General (Unknown) (On-Prem) | VRAS for: The Christ Hospital / PeriGen | CA-8.1 Perform penetration testing on internal networks at least annually. | Provide Policy/Procedure/Process for internal penetration testing. Provide evidence of most recent internal penetration exercise | High | 2019-12-31 |  |  |  | sent to vendor
eedfcd85-9cdb-e911-a9a9-000d3a324ed7 | F0uccEzD2Kt6HseVh88T8jWW5guWOl/bQTEUT/bcAfOwVbb7hsmIsQzseTWSTuA/QLUiage5vVLC6LJ1cyP+kQ== | 2019-09-20 11:48 | General (Unknown) (On-Prem) | VRAS for: The Christ Hospital / PeriGen | SA-5.4 Protect information system documentation as required and only distributed to authorized personnel. |  | Low | 2019-12-31 |  |  |  | sent to vendor
efdfcd85-9cdb-e911-a9a9-000d3a324ed7 | 4EOzC/RtzwO30tSIZeXFl0Onge9rjkJcniBWb951tjqDxz7VSUgT/2ub04l4addZcBXT6mgle7BwrvSfKVvZoA== | 2019-09-20 11:48 | General (Unknown) (On-Prem) | VRAS for: The Christ Hospital / PeriGen | SA-1.1 Develop and implement formally documented policies and procedures for System and Services Acquisitions. |  | Low | 2019-12-31 |  |  |  | sent to vendor
f0dfcd85-9cdb-e911-a9a9-000d3a324ed7 | PhrO1glysbjvgtGfjZXihJrlVTuzMQhzBYeID/HoO4efdX5fX25lDNDzZStkgea8VmtWbc/W9VgNtoAJ2Upb7g== | 2019-09-20 11:48 | General (Unknown) (On-Prem) | VRAS for: The Christ Hospital / PeriGen | SC-1.1 Develop and implement policies and procedures for System and Communications Protection. |  | Low | 2019-12-31 |  |  |  | sent to vendor
b9e65b84-9cdb-e911-a9a5-000d3a324f4c | yqQK8ZYgK+Xgsv93ZzUw7kAOzGQVwLE/EtWiGldFUGjzugV2CSCVa+nD0A8qY6YKXNgyxDvGPG1kR1oOmFGB4Q== | 2019-09-20 11:48 | General (Unknown) (On-Prem) | VRAS for: The Christ Hospital / PeriGen | SC-8.2 Implement cryptographic mechanisms to recognize changes to information during transmission. | Provide policies/procedures regarding security of data transmission Provide Policy/Procedures for data encryption Provide screen shot of server supported encryption protocols. | High | 2019-12-31 |  |  |  | sent to vendor
c4e65b84-9cdb-e911-a9a5-000d3a324f4c | dbBA9pVvB3RXuGwCq25BjX2XuKVj6Rp7kHABWepNhmyV2j/QIJ9Hmju1OuHM8UdpYJK84ryFnuZRW9z4xjjUCw== | 2019-09-20 11:48 | General (Unknown) (On-Prem) | VRAS for: The Christ Hospital / PeriGen | SC-10.1 Configure the information system to terminate network connections associated with a communication session at the end of the session or after no longer than 30 minutes of inactivity. |  | Low | 2019-12-31 |  |  |  | sent to vendor
c5e65b84-9cdb-e911-a9a5-000d3a324f4c | klz128J2mKm9ShEbYan/iZFkg1GopFG6ekS1ez3ofiw/sx3FPfaQlRGNKYv+F7I6m0Ltur4JojykJd2TYfp7Gw== | 2019-09-20 11:48 | General (Unknown) (On-Prem) | VRAS for: The Christ Hospital / PeriGen | SI-1.1 Develop and implement policies and procedures for System and Information Integrity. |  | Low | 2019-12-31 |  |  |  | sent to vendor

## hiddenSheet (hidden)
ct_vrasriskstrategyrecommendation:bBL/Utv5tamGKYJXdOd21hyYdoiIjyU3WlSmitvAQPYZ3EYdzD9cncIu/NW00KvLKIk11fdeEOIbbXS6oe5TMw==:ct_vrasriskstrategyrecommendationid=%28Do%20Not%20Modify%29%20Risk%20Strategy%20Recommendation&checksumLogicalName=%28Do%20Not%20Modify%29%20Row%20Checksum&modifiedon=%28Do%20Not%20Modify%29%20Modified%20On&ct_environment=Environment&ct_vrasid=VRAS%20Name&ct_vendorsecurityriskstrategyrecommendation=Vendor%20Security%20Risk%20Strategy%20Recommendation&ct_documentationrequest=Documentation%20Request&ct_riskreductionimpact=Risk%20Reduction%20Impact&ct_recommendedduedt=Recommended%20Due%20Date&ct_remediationstrategyacceptedbyvendor=Remediation%20Strategy%20Accepted%20by%20Vendor&ct_contractuallyagreeduponcompletiondate=Contractually%20Agreed%20Upon%20Completion%20Date&ct_vendornotes=Vendor%20Notes&ct_newriskstrategystatus=Risk%20Strategy%20Status
Yes | No
Client Accepted Risk | Control Satisfied | Control Not Satisfied | Control Not Applicable | Accepted | Not Accepted | Sent to Vendor | Evidence Requested