## Sheet1
Paragraph | Requirement | Frequency | Status
HIPAA-WI-001 para 1. | All Workforce Members will sign the Workforce Member HIPAA Compliance and Confidentiality Statement provided below prior to being given access to PHI, ePHI or ePHI Systems and annually thereafter | Annual | Missing - see email sent out earlier Israel - Done North Am - TBD (Candace)
HIPAA-WI-003 para 1.3.1 | The Privacy & Security Officer will assess and determine, on a yearly basis, those Workforce Members who require access to PHI in order to carry out their job functions. | Annual | Done Nov 5, 2020, use as model ongoing
PeriGen will document its Workforce Members’ access to PHI.
HIPAA-WI-003 para 1.3.2 | On an annual basis, the Privacy & Security Officer will: | Annual | No documentation found. Make statement that there are no such requests or activities (Bruno)
a. Assess and determine all routine and recurring disclosures requested or made by PeriGen.
b. Compose and complete a disclosure survey that identifies all routine and recurring disclosures.
HIPAA-WI-004 para 2.3.1 | At least once per year, PeriGen will convene a workgroup and/or engage outside assistance to conduct an accurate and thorough assessment of the potential risks and vulnerabilities to the confidentiality, integrity, and availability of ePHI and ePHI Systems accessed, used by, owned or operated by PeriGen | Annual | No documentation found Create a report breaking down all cases of ePHI that is stored, is it secured? how? Document criticality (Bruno)
PeriGen will create a Risk Management Plan to address risks identified in the annual Risk Analysis
HIPAA-WI-004 para 4.2 | Audits of email and complaint documentation will be conducted every 12 months | Annual | No documentation found - Andrew: Are checks being done to scrub ePHI when tickets are reviewed/closed. - Bruno: Audit to be done by June 1
HIPAA-WI-004 para 6.3 | PeriGen will undertake periodic evaluations of its security safeguards at intervals determined by the Privacy & Security Officer based on the specific triggers and the characteristics of each ePHI System. (at least annually) | Annual | No documentation found Make statement that there are no such ePHI systems (Bruno)
PeriGen will periodically evaluate its ePHI Security Policies on a annual basis
HIPAA-WI-004 para 7.3 | PeriGen will review these Security Policies and Procedures at least once per year as part of its annual risk analysis | Annual | HIPAA policies approved March 2020, due for review by March 2021 - For 2021, claim last modification consists of review - Annual review of applicable group - June 1st. Capture minutes for records.
HIPAA-WI-005 para 2.3.2 | PeriGen will review access privileges to ePHI annually | Annual | Duplicate of HIPAA-WI-003 para 1.3.1 – Done Nov 5, 2020
HIPAA-WI-006 para 8.3 | PeriGen will conduct a yearly data criticality analysis as part of its risk assessment in accordance with the Security Risk Management Policy | Annual | No documentation found - Captured by item HIPAA-WI-004 para 2.3.1 - To be reviewed in annual review meeting
HIPAA-WI-006 para 11.3.1 | PeriGen will take an inventory of hardware and electronic media that contain ePHI every six months | Six-monthly | Done Dec 2020 but not documented - File audit/research done for project X
HIPAA-WI-006 para 10.2 | PeriGen will periodically review (quarterly), and may modify as appropriate, the permitted and prohibited uses of Workstations and the security controls implemented to protect Workstations in accordance with the Security Risk Management Policy | Quarterly | No documentation found - Revise policy for annual instead of quarterly - Need to combine Vector reports with what is available in Israel, document security controls - Target for Jun 1